Agenda & facilitation steps

| Timing | Workshop elements | Preparations |
| --- | --- | --- |
| 60 min | Opening session | - Slides - Projector - Sound system for videos - Flipchart or Whiteboard - Paper - for flipchart and teams - Pens - for flipchart and team members - Post-it notes - Copies of the Project charter - Refreshments & Lunch |
|  | Clarifying the challenge |  |
|  | What is a 30 Day Project? |  |
|  | The Journey of the 30-Day Team |  |
|  | The work we will be doing today |  |
| 15 min | Comfort Break |  |
| 60 min | Setting our 30-Day goal |  |
| 30 min | Shaping our Team Agreement |  |
| 15 min | Break |  |
| 60 min | Developing our 30-Day Workplan |  |
| 30 min | Feedback and Close-up |  |

Timing is a guideline - it could be shorter or a bit longer, depending on the topic and the team.

Below is a step-by-step guide for presenting this segment of the agenda. This step-by-step guide aligns with the slides in the presentation deck provided in the Guidance Notes. This is intended for and addressed to the Team Coach. But it could be used by anyone leading this segment of the agenda.

Opening session - Welcome and Warm-up (15 min)

- Welcome everyone, including the Project Sponsor and other leaders and share the workshop agenda. - Warm-up exercise to create an energised environment. Use whatever works for you. One suggestion is to ask everyone to pair up with someone else to share perspectives on these two questions and then call on some participants to share highlights in the plenary. - What do I hope will happen today? - What special skill outside my job am I bringing to the Team?

Clarify the Focus of the Team (15min)

- Ask the Project Sponsor to provide a 5-minute overview: - Setting the context – localising the strategy - Recap the focus area and explain why it was chosen. - Clarify why these team members were chosen. - Clarify what is expected of the team. - Questions and answers: Allow team members time to think of questions and write them down on Post-it Notes. Then, as a Team Coach, read each question and invite the Project Sponsor and/or other leaders to respond. - Thank the leaders for taking the time and for their willingness to be ‘put on the spot’. Remind them to rejoin the team to provide feedback on the goal and plan during the last session of the workshop. And make sure to let them know they are welcome to stay a little while longer if they have time.

What is a 30-Day Project? (2omin)

- Explain that the 30-Day Project is a special type of project. Show the slide entitled: What is a 30-Day Project? - “So let’s explore what is different about it…”. Show part 1 of the intro video. Pause after the video and ask participants to share experiences that they may have had in similar crisis situations, and how performance and behaviour changed in these. - Summarise what is unusual about a 30-Day Project by showing the slides on “unusual behaviours”. - Unique Features: Show the second video about the events and the enabling environment.

The Journey of the30-Day Team (5 min)

- “So you may be asking, what are we going to do over the next 100 days, and what is our role?” Share the slide on the events in the 30-Day Project, and indicate that with the Start-Up workshop today, the 100-day countdown will start tomorrow. - Share the slide on the team to clarify the roles of Project Sponsor, Team Members and Team Coach. This is a good slide to use for the next step of transitioning.

The work we will be doing today (5 min)

- “So you may be asking, what do we need to do today?” - “We will set our 30-Day Goal. - We will create a team agreement outlining how we, as a team, will work together over the next 30 days. - Based on our goal, we will develop our 100-Day Plan.” - “This is the work we will be doing today. But before we shape our 30-day goal, let’s pause to see what questions you may have about 30-Day Project and how they are similar and different from regular projects.” - If you feel there is confusion and people are not sure what to ask, invite them to take 5 minutes in small groups to talk about the videos and identify questions that they would like clarification on before proceeding to the next agenda item.

Setting our 30-Day Goal (60 min)

“Setting the 30-Day Goal is the most important step in the Start-Up Workshop. Committing to a shared goal, especially one that feels scarily ambitious, binds the group together and sets the stage for them becoming a team. STEP 1 - Results orientated goal Go over the examples and criteria for a good 30-day goal. Emphasise that the goal templates are oriented towards an outcome or result (not a plan, not a recommendation, not an activity or a task to complete). (5 min) Emphasise the differences between SMART (Specific, Measurable, Achievable, Relevant, Time-bound) and SMURF goals. Not all SMART goals are Results-Oriented. SMURF goals always are. SMART goals are Achievable. SMURF goals are unreasonable and bordering on the impossible! STEP 2: Shaping the team’s 30-Day Goal Two slides in the slide pack have templates of these same goals, with blanks that the team will fill out during this critical step of this agenda item. Go over these examples and templates with the Project Sponsor, and pick/customise one or two that best suit the Heath Check survey issue highlighted in the Project Charter. - Two slides in the slide pack have templates of these same goals, with blanks that the team will fill out during this critical step of this agenda item. Go over these examples and templates with the Project Sponsor, and pick/customise one or two that best suit the Heath Check survey issue highlighted in the Project Charter. - Ask them to discuss these to see if which one they are comfortable with. If need be, customise one of these with them. Making sure they agree on how progress towards the goal will be measured. (20 min) - For the selected template, ask the team to fill in the blanks with numbers or percentages that represent how ambitious they would like to be in the next 100 days. After some initial discussion, you can ask each team member to write down a number or a percentage on a post-it note; then, they can share these and discuss. Use voting if need be. Remember that we are not seeking consensus but rather the willingness of each team member to work towards achieving this Goal. Naturally, if they feel that it is “pie in the sky”, they will not take it seriously. They need to believe that it is possible to achieve it, however remote that possibility may be. Leave room for discussion and argument. It is essential that everyone feels heard before agreeing on a 30-Day Goal. Keep reminding the team that the leaders encouraged them to set highly ambitious goals. Remind them about the goals they heard about in the videos. STEP 3 - Refining the goal. More often than not, the team will be so eager to move on to the Work Plan that they fail to ask important questions about their 30-Day Goal (15 min): - Compared to the baseline in the GBVF Health Check survey, does the goal feel really “unreasonable”? - When will we start measuring progress towards the goal? And how often will we measure progress after that? You might suggest that the team conduct a weekly random survey specifically focused on the targeted behaviour so that they can track progress every week. You can use Mentimeter to make it fun, simple, and fast. - Is the goal framed as “In 30 days,… OR “Within the last week of the 30 days…?” OR “During the 30 days after the Challenge…” Which framing is most suitable? - What are the possible adverse consequences of pursuing this goal? What are the ways to ensure that the team mitigates these? For example, if the goal is to develop a policy within 30 days and the HR department is involved, how can we ensure that they do not drop all their other priorities to focus on developing the policy? This step will help you guide the team as they discuss these questions so they can refine and, if need be, adjust their 30-Day Goal. After the preliminary goal is set, we suggest that you congratulate the team on completing the toughest part of the Start-up workshop and give them a short break.

Shaping our Team Agreement (30min)

Now that the team has set their goal, you will help them create a team agreement. This is intended for and addressed to the Team Coach. But it could be used by anyone leading this segment of the agenda. STEP 1: Electing Team Leader - Share the Team Leader Role: - Helps the team stay organised and focused on the Goal - Coordinates, as needed, with the Project Sponsor - Leads weekly team meetings - Elect the Team Leader: Inform team members that they will practice self-governance for 30 days. Part of this is electing their own Team Leader. Ask each Team member to submit 1 or 2 names on a post-it note (they can nominate themselves). Count the votes discreetly and ask the selected leader if they accept. Announce and celebrate. STEP 2: Develop the Team's Operating Agreement - Develop a Team Operating Agreement to help establish how the team will work together. Ask the team to decide on the questions in the slides. - Before the team discusses the first question about roles, explain to the team what is expected from each role: - Data Geek: Updates performance data in the goal tracker. - Storyteller: Coordinates with the World of Impact communications team to relay the team’s stories of success and struggles. - The Team Leader can now take charge and ask specific team members if they would like to play each of these roles.

Developing our 30-Day Workplan (60min)

If the 30-Day Goal is the equivalent of the Team’s mission and purpose, the Work Plan is the equivalent of its strategy. This Learning Deep Dive is primarily addressed to the Team Coach. Naturally, others can use it if they are filling in for the Team Coach. We suggest you use 5 steps to help the Team develop its 100-Day Plan. STEP 1 - Generating Ideas (15 min) Start by brainstorming on a flip chart using Post-it notes. - Hand each team member a packet of post-it notes and a pen. Ask them to think about actions, ideas, or strategies that can help them make progress towards the 30-Day Goal. Ask them to write one action/idea/strategy on a post-it note. - After a brief period of idea generation, ask the group to look at the wall of Post-it notes to see if this inspires additional ideas. You can conduct another round of individual “ideation” using Post-it Notes. If the ideas are all related to doing things a little better, challenge them to come up with completely new ideas. STEP 2 - Cluster Ideas (10 min) Ask the group to start clustering the post-its that go together. Ask the group to label each cluster with a heading that best describes the cluster. The post-its on the slides are just examples. The headings will become work streams (step 3) in the plan, and most post-its will become action steps (step 4) in that work stream. Step 3 - Creating Planning Swimlanes (20 min) - Before the session, you need to create a blank timeline with several “swim lanes” on flip charts (see the diagram below). Each swim lane will be populated with post-its from one cluster of ideas. Once these post-its are turned into actions, we will refer to each swim lane as a “work stream” (for tips on how to do this, watch the video below: Creating Planning Swim Lanes. - Ask team members to split into two or three subgroups, each focused on one or two clusters of ideas. - Each subgroup discusses the post-it notes in each of their clusters, consolidates some of them if needed, and turns each into an action step. Then, they move them to the corresponding swim lane, placing them in the right time frame. They can also begin assigning team member names to each one (one name per post-it note). - The whole team does a “stress-test” to the emerging plan, represented by these post-it notes in the swim lanes. “Does completing these action items give us high confidence that the Goal will be achieved”? If the answer is no, challenge the team to identify missing work streams and identify action steps within this. Step 4 -Reviewing and refining the plan (20 min) - Sub-groups add names and dates to each post-it note in the swim lanes. - The whole team reviews all the swim lanes’ timelines to identify any gaps, excessive action steps within a single timeframe, or if actions across swim lanes need to be better aligned. They discuss and make adjustments as needed. - Ask for a volunteer to transcribe the timeline into a work-planning template. This will be the first version of the Team’s work plan.

Feedback and Close-up (30 min)

- Feedback to the Project Sponsor: The Team Coach welcomes the Sponsor back, and the Team Leader reads out the 30-Day Goal, providing a few highlights of the Plan. These might include: - What is particularly exciting to the team about the plan (e.g. innovative ideas they want to test)? - What is worrisome? - What support do they need from the mentor and other leaders in the organisation? - What advice would they like from the Sponsor? - Other team members can pitch in if time permits. The Project Sponsor comments and responds. - Onwards: The Team Coach outlines the way forward: - Weekly team meetings. - Weekly check-in between the Team Leader and Sponsor - The Refresh Workshop, where the Team and the Sponsor take a step back to reflect and adjust the plan as needed. - Scale-Up Workshop to celebrate and chart the way forward. - Workshop Feedback: The Team is to complete the short workshop feedback survey to help identify improvements for the next workshop. - Appreciations: Team members think of others on the Team who have made a unique contribution during the workshop that merits acknowledgement and appreciation. It could be: - They made it easy for someone else on the team to speak up. - They offered a brilliant idea. - They encouraged the team to think big. - They said something that others were thinking but were reluctant to say out loud. - Closing Comments: The Project Sponsor makes a closing comment. Each team member can share a word or two that expresses how they feel at the end of the workshop. - Group Photos: Take a group photo, with and without the Project Sponsor. Also, take photos of the 30-Day Goal and Plan (if on a flip chart), in case these get lost.